## Yomin_Marketing_Launch_Plan
Section | Channel/Action Item | Objective/Description | Content Type/Deliverable/Target
1. Multi-Channel Strategy | LinkedIn | Lead Gen & Authority | Case Studies, Industry Reports, AMI Systems Whitepapers | Utility Directors, Electrical Engineers, Procurement Managers
| YouTube | Trust & Technical Proof | Factory Tours, Product Stress Tests, IoT/Smart Meter Tutorials | Technical Consultants, R&D Teams, Large Scale Distributors
| Facebook | Global Awareness | Product Highlights, Trade Show Recaps, Multi-language Support | Electrical Contractors, Regional Distributors, Middle-market SMEs
2. Launch Timeline - Phase 1 (Weeks 1-2) | Social SEO Optimization | Update LinkedIn/FB with keywords: IEC 62053, Smart Metering, AMI Systems. | Optimized Profiles
| Lead Magnet Creation | Draft 2026 Smart Grid Efficiency Guide for LinkedIn lead ads. | PDF Whitepaper
| Video Scripting | Storyboard a 2-minute 30 Years of Precision brand film. | Production Scripts
2. Launch Timeline - Phase 2 (Weeks 3-4) | Inside Yomin Teasers | 15-second clips of the metal deep processing line and QC labs. | YouTube Shorts / FB Reels
| Polling the Industry | Ask LinkedIn: What is your biggest challenge in AMI deployment? | LinkedIn Posts
| Standard Compliance Series | Static images highlighting IEC/ANSI/KEMA certifications. | Facebook / LinkedIn
2. Launch Timeline - Phase 3 (Weeks 5-6) | Main Brand Film Launch | Hero video showcasing factory scale and global footprint. | YouTube / LinkedIn Ad
| LinkedIn Lead Gen Ads | Download our AMI integration manual targeted by job title. | SQL (Sales Qualified Leads)
| FB Global Catalog Ad | Dynamic ads showcasing top 10 energy meters to regional interests. | Website/Alibaba Traffic
2. Launch Timeline - Phase 4 (Weeks 7+) | Client Success Stories | Video interviews or PDF slides of successful utility deployments. | Bi-weekly
| Live Q&A / Webinars | The Future of IoT Metering technical session. | Monthly
| Retargeting Ads | Target users who visited the Alibaba store but didn't inquire. | Ongoing
3. Execution Checklist - Technical | LinkedIn Insight Tag | Connect to yominelectric.com
| Facebook Pixel | Connect to yominelectric.com
| RFQ Tracking | Setup on Alibaba store links
| Content Repository | Create Google Drive/Dropbox for assets
3. Execution Checklist - Creative | Factory B-roll | Shoot SMT lines, testing labs
| Product Photography | DIN Rail Meters, Smart Meters, Transformers
| Branded Templates | Design for Technical Specs social posts
3. Execution Checklist - Channel Specific | LinkedIn | Follow 50 target utility procurement influencers
| LinkedIn | Join 5 relevant groups (Smart Grid, Meter Data)
| YouTube | Create custom thumbnails with high-contrast text
| YouTube | Translate captions (French, Spanish, Arabic)
| Facebook | Setup Auto-Responder for Messenger
| Facebook | Create Yomin Global Partner community group
4. KPIs | LinkedIn | Goal = 20 High-Quality Leads (MQLs) per month
| YouTube | Goal = 1,000+ Average Views; High engagement rate
| Facebook | Goal = 15% increase in traffic; 50+ new inquiries
| Overall | Brand sentiment score and Inquiry to Sale rate